## Sheet1
Tasks | Date Started | Date Finished | Functionality Progress | Design Progress | Responsible Coder | Comments
Timetabler - Rounds
View, add, edit and delete requests made by that timetabler | 2015-04-02 |  | 40% |  | Prakash | Scaffolded, i/o needs to be improved
When viewing, should be able to sort/filter requests by appropriate fields |  |  | 0%
View requests that have been sent back by the central admin and edit/resubmit as required. | 2015-04-02 |  | 10% |  | Prakash | Scaffolded, i/o needs to be improved (colours for statuses)
Should be able to sort/filter requests by appropriate fields |  |  | 0%
Timetabler - Ad-Hoc
View, add, edit and delete requests made by that timetabler | 2015-04-02 |  | 40% |  | Prakash | Scaffolded, i/o needs to be improved
When viewing, should be able to sort/filter requests by appropriate fields |  |  | 0%
View requests that have been sent back by the central admin and edit/resubmit as required. | 2015-04-02 |  | 5% |  | Prakash | Scaffolded, i/o needs to be improved (colours for statuses)
Should be able to sort/filter requests by appropriate fields |  |  | 0%
Timetabler - Other
View last year’s requests and edit/resubmit as required. |  |  | 0%
When viewing, should be able to sort/filter requests by appropriate fields |  |  | 0%
View timetables for members of staff |  |  | 0%
View timetables for each degree (e.g. Computer Science and Maths in Part B) |  |  | 0%
Change which lecturers are associated with a module |  |  | 0%
Change which module are associated with each degree program |  |  | 0%
View, add, edit and delete private rooms |  |  | 0%
View pool rooms | 2015-03-27 |  | 70% |  | Prakash | Scaffolded but main functionality complete, improve i/o
Must be able to filter rooms by location, capacity and facilities |  |  | 0%
Creating Requests | 2015-04-02 |  | 30% |  | Prakash | Scaffolded, i/o needs to be improved
Specify what facilities, if any, are wanted in that request |  |  | 0%
Specify one or more room wanted in that request |  |  | 0%
When specifying the room, must be given the option of specifying just a park or “Any” |  |  | 0%
When specifying the room, must be allowed to check the availability of a room by date |  |  | 0%
When specifying the room, must be allowed to check the availability of a room by room |  |  | 0%
Must be able to select any combination of weeks |  |  | 0%
Must be able to specify what module the request is being made for | 2015-04-02 |  | 70% |  | Prakash | saving has not been tested and probably needs some work in the controller
Must be able to specify which period the request is for and how long the session will be | 2015-04-02 |  | 60% |  | Prakash | haven't done session length since this needs to be dynamic
Must be able to add any comments in the form of special requirements | 2015-04-02 |  | 60% |  | Prakash | i/o needs to be improved (this is in the partial view)
Central Admin
Do everything a timetabler can do |  |  | 30% |  | Prakash | This will probably be done with action links
View, edit and delete pool rooms | 2015-03-27 |  | 60% |  | Prakash | Scaffolded, i/o needs to be improved and cannot edit facilities of a room
View, edit and delete facilities in the database | 2015-03-27 |  | 75% |  | Prakash | Scaffolded, i/o needs to be improved
Allocate requests by changing the status of the request |  |  | 0%
Must be able to change room on request before allocation |  |  | 0%
Add, view, edit and delete rounds | 2015-03-27 |  | 95% |  | Prakash | validation required
The System
Differentiate between timetablers and the central admin, i.e. timetablers must not have access to central admin features | 2015-03-27 |  | 60% |  | Prakash | This is simple enough to do using the [Authorize] tag
Block timetablers from booking other department’s private rooms |  |  | 0%
Immediately allocate a request if it is for a private room |  |  | 0%
Multi-room requests including a private room will be treated as normal and can only be allocated by the central admin |  |  | 0%
Immediately allocate an ad-hoc request |  |  | 0%
Be portable and accessible |  |  | 0%
Implement rounds |  |  | 0%
The central admin can only allocate requests from a round that has ended |  |  | 0%
All requests in round 1 are priority requests |  |  | 0%
Validate all user input |  |  | 0%
Set default values on all fields |  |  | 0%
Allow the user to authenticate themselves using a password | 2015-03-25 |  | 95% |  | Prakash | Need to create other uses in the database (only CA and CO exist)