## Sheet1
Tasks | Date Started | Date Finished | Functionality Progress | Design Progress | Responsible Coder | Comments
Timetabler - Rounds
View, add, edit and delete requests made by that timetabler | 2015-04-02 | 2015-05-02 | 100% |  | Prakash | multiple "Any room in park/building" rooms cannot be added. Not sure how to get around thing as it’s a problem with adding it to the database
When viewing, should be able to sort/filter requests by appropriate fields | 2015-04-27 | 2015-05-02 | 90% |  | Dan | requestId
View requests that have been sent back by the central admin and edit/resubmit as required. | 2015-04-02 | 2015-05-05 | 80% |  | Prakash | Scaffolded, i/o needs to be improved (colours for statuses)
Timetabler - Ad-Hoc
View, add, edit and delete requests made by that timetabler | 2015-04-02 |  | 95% |  | Prakash | Scaffolded, i/o needs to be improved
When viewing, should be able to sort/filter requests by appropriate fields | 2015-04-27 | 2015-05-02 | 90% |  | Dan
View requests that have been sent back by the central admin and edit/resubmit as required. | 2015-04-02 | 2015-05-02 | 80% |  | Prakash | Scaffolded, i/o needs to be improved (colours for statuses)
Timetabler - Other
View last year’s requests and edit/resubmit as required. |  |  | 0%
View timetables for members of staff |  |  | 0%
View timetables for each degree (e.g. Computer Science and Maths in Part B) |  |  | 0%
Change which lecturers are associated with a module | 2015-04-28 | 2015-04-28 | 100% |  | Prakash
Change which module are associated with each degree program | 2015-04-29 | 2015-04-29 | 100% |  | Prakash
View, add, edit and delete private rooms |  |  | 0%
View pool rooms | 2015-03-27 | 2015-04-27 | 100% |  | Prakash
Must be able to filter rooms by location, capacity and facilities | 2015-04-27 |  | 5%
Creating Requests | 2015-04-02 | 2015-05-02 | 100% |  | Prakash
Specify what facilities, if any, are wanted in that request | 2015-04-13 | 2015-04-15 | 100% |  | Prakash | Could implement hide/show to hide unpopular facilities
Specify one or more room wanted in that request | 2015-04-16 | 2015-04-17 | 100% |  | Prakash
When specifying the room, must be given the option of specifying just a park or “Any” | 2015-04-16 | 2015-04-17 | 100% |  | Prakash
When specifying the room, must be allowed to check the availability of a room by date |  |  | 0%
When specifying the room, must be allowed to check the availability of a room by room |  |  | 0%
Must be able to select any combination of weeks | 2015-04-12 | 2015-04-15 | 100% |  | Prakash | Uses selectable week selector
Must be able to specify what module the request is being made for | 2015-04-12 | 2015-04-13 | 100% |  | Prakash
Must be able to specify which period the request is for and how long the session will be | 2015-04-02 | 2015-04-15 | 100% |  | Prakash
Must be able to add any comments in the form of special requirements | 2015-04-02 | 2015-04-14 | 100% |  | Prakash | limit the size of the input maybe?
Central Admin
Do everything a timetabler can do |  |  | 70% |  | Prakash | This will probably be done with action links and [Authorize] tags
View, edit and delete pool rooms | 2015-03-27 | 2015-04-24 | 100% |  | Prakash | Scaffolded, i/o needs to be improved and cannot edit facilities of a room
View, edit and delete facilities in the database | 2015-03-27 | 2015-04-24 | 100% |  | Prakash | Scaffolded, i/o needs to be improved
Allocate requests by changing the status of the request | 2015-05-01 | 2015-05-01 | 100% |  | Prakash
Must be able to change room on request before allocation | 2015-05-01 | 2015-05-01 | 100% |  | Prakash
Add, view, edit and delete rounds | 2015-03-27 | 2015-04-02 | 100% |  | Prakash
The System
Differentiate between timetablers and the central admin, i.e. timetablers must not have access to central admin features | 2015-03-27 |  | 60% |  | Prakash | This is simple enough to do using the [Authorize] tag
Block timetablers from booking other department’s private rooms |  |  | 0%
Immediately allocate a request if it is for a private room |  |  | 0%
Multi-room requests including a private room will be treated as normal and can only be allocated by the central admin |  |  | 0%
Immediately allocate an ad-hoc request |  |  | 0%
Be portable and accessible |  |  | 0%
Implement rounds |  |  | 0%
The central admin can only allocate requests from a round that has ended |  |  | 0%
All requests in round 1 are priority requests |  |  | 0%
Validate all user input |  |  | 0%
Set default values on all fields | 2015-04-12 |  | 60% |  | Prakash | in request, all fields have default values
Allow the user to authenticate themselves using a password | 2015-03-25 |  | 95% |  | Prakash | Need to create other uses in the database (only CA and CO exist)